## Slide 1
LEISH.MY · LAUNCH MARKETING PLAN · 90 DAYS
Medium Budget
Never DM for a Date Again. — official launch October 5, 2026
TOTAL BUDGET
RM 40,000
DAY-90 HEADLINE
800 clients · 40–45 artists · 15–20 bookings/wk
LAUNCH DATE
Oct 5, 2026
Founder + one part-time marketer. Co-hosted pop-up launch, one micro-KOL wave, Meta + narrow Google. Lean execution, same wedding-season timing.

## Slide 2
EXECUTIVE SUMMARY
The Play — Medium Budget
FOCUS
Lean paid, high intent
Meta RM 12k + Google RM 4k (brand + top-10 keywords). No TikTok ads. Retargeting gets 20% of Meta budget. Every ad set gated at 2x ROAS after 2 weeks.
STYLE
Co-hosted pop-up launch
Partner studios host the venue; Leish! brings booking tech + offers. One wedding expo OR pop-up — decide by lead-cost projection by Sep 15.
GROWTH LOOP
Commission-heavy KOLs
6–8 micro creators (10k–50k), 50% flat / 50% booking-code commission (10% of GMV) so they self-motivate. One wave, then referral program from Day 30.
Artist gate before Day 0: 25 bookable artists by Sep 28 · Campaign: Never DM for a date again · Hero categories: Bridal · Hijab · Event

## Slide 3
RM 40,000 · 90 DAYS
Budget Breakdown
Meta ads (IG + FB, incl. 20% retargeting)
RM 12,000
30%
KOLs — 1 wave, 6–8 micro (10k–50k)
RM 10,000
25%
Events — 1 co-hosted pop-up OR 1 wedding expo
RM 6,000
15%
Google Search (brand + top-10 keywords)
RM 4,000
10%
Community / campus seeding
RM 3,000
8%
Artist acquisition (concierge + referral)
RM 3,000
8%
PR (direct pitching), design & tools
RM 2,000
5%
Payback logic: CAC ≤ RM 25 → client LTV RM 90–150 (2–3 bookings × RM 300 × 20%). Payback in 1–2 bookings; ROAS gate ≥ 2.5x.

## Slide 4
NORTH-STAR METRIC: COMPLETED BOOKINGS PER WEEK
Day-90 Targets
800
Registered clients
40–45
Active artists & studios
15–20
Bookings / week
RM 4.5–6k
GMV / week
≤ RM 25
Client CAC (paid)
≥ 2.5x
Blended ROAS
PROGRESSION
KPI | Pre-launch | Day 30 | Day 60 | Day 90
Waitlist / clients | 1,000 waitlist | 300 | 550 | 800
Weekly bookings | — | 6–8 | 12 | 15–20
Commission / wk (20%) | — | RM 400 | RM 700 | RM 900–1,200
Email list | 1,500 | 2,000 | 2,500 | 3,000
Social following | 1,500 | 2,500 | 3,800 | 5,000

## Slide 5
TIMELINE
Four phases
PHASE 0 · PRE-LAUNCH
Aug 10 – Oct 4
Green-light Aug 10
Waitlist live Aug 31 (RM30 offer)
25 anchor artists, concierge
Teaser content 2x/wk
KOLs contracted by Sep 21
Paid test Sep 28
PHASE 1 · LAUNCH WEEK
Oct 5 – 11
Co-hosted pop-up with partner studios
6–8 micro KOLs post
Direct-journalist PR pitch
Meta + Google full ON
LEISH30 live
PHASE 2 · WEDDING SEASON
Oct 12 – Dec 31
Referral program Day 30 (RM15/RM15)
1 expo booth OR 2 campus pop-ups
Hijab community push (Nov)
B2B light — 2–3 pitches
1 blog/mo SEO
PHASE 3 · REVIEW
Jan 2027
Score vs Day-90 targets
≥12 bookings/wk + CAC ≤ RM 25 →
upgrade to High for CNY
else fix or downgrade

## Slide 6
CHANNEL MIX
Owned · Paid · Earned
OWNED — FOUNDATION
IG — 3–4 posts + 7 stories + 1 reel / wk
TikTok — 2 reels / wk (repurposed)
FB + bridal/beauty groups — daily
Email (Brevo) — sequence + 1 newsletter/mo
WhatsApp — confirmations + monthly broadcast
SEO — 1 blog/mo on /inspiration + /events
Artist share links — always-on loop
PAID — RM 16K
Meta RM 12k — bridal/beauty stacks, KL-Selangor, 20–40
Retargeting = 20% of Meta budget
Google RM 4k — brand + top-10 high-intent keywords
No TikTok ads at this tier
Kill any ad set <2x ROAS after 2 weeks
EARNED + COMMUNITY — RM 19K
6–8 micro KOLs — 50/50 flat + booking commission
1 co-hosted pop-up OR 1 wedding expo
2 campus pop-ups — Cyberjaya (MMU, Limkokwing)
Direct PR pitch — SAYS, The Star, Malay Mail
Bridal FB group giveaways (RM 500)

## Slide 7
LOCK BEFORE DAY 0
Launch Offers & Promotions
CLIENT SIDE (DEMAND)
LEISH30
RM30 off first booking · cap 150 · valid to Day 30
Early-bird bonus
Waitlist members get RM30 + priority access
Refer-a-friend
RM15 credit each · live from Day 30
ARTIST SIDE (SUPPLY)
Free 3-month Pro listing
Normally RM 200–500/mo · cap 30 artists
0% commission, first 10 bookings
vs standard 20% · cap 20 artists
Artist referral
RM100 + featured slot on referee's 5th booking
⚠ Pre-launch dev task: verify promo-code / credit support in admin before Aug 24 (same as High tier).

## Slide 8
WATCH WEEKLY
Risks & Mitigations
Small team = content slippage
Batch content weekly (2 blocks/wk); templates; outsource design per-asset.
Only 1 KOL wave
Commission-heavy 50/50 deals; secure 2-month UGC rights in contracts.
Thin paid budget
Kill <2x ROAS ad sets after 2 weeks; 20% of Meta budget to retargeting.
Artist gate not met (25)
Start concierge Aug 31; fallback: extend free Pro to 6 months.
Pop-up vs expo choice
Decide by lead-cost projection; book by Sep 15.
Guardrails: artists idle 14+ days · no-show <15% · artist response <4 hrs · search→booking ≥2%

## Slide 9
OWNER CHECKLIST + UPGRADE PATH
Execute · Measure · Decide
30-DAY CHECKLIST
Aug 10
Confirm date + budget
Aug 24
Part-time marketer hired
Aug 31
Waitlist + RM30 offer live
Sep 21
KOL wave contracted (6–8)
Sep 28
25 anchor artists (gate!)
Oct 5
DAY 0 — launch
UPGRADE / DOWNGRADE
Upgrade
Day-60: ≥12 bookings/wk + CAC ≤ RM 25 + artist retention ≥ 80% → scale to High (RM 96k) for CNY season.
Downgrade
Day-30: paid CAC > RM 35 → cut Google + half of Meta; shift to community channels.
REMAINING CHECKLIST
Nov 4
Referral live · Day-30 review
Dec 4
Day-60 checkpoint → upgrade decision
Jan 4
Day-90 review + Q1'27 plan
GA4/Meta events verified Aug 31 · paid test Sep 28 → full Oct 5 · pop-up/expo locked by Sep 15.

## Slide 10
Growth, with discipline.
Full plan: docs/launch-marketing-plan-medium.md · Tiers: docs/launch-marketing-plan-tiers.md
Next step: close the 5 tier risks and execute the 12-item checklist; Day-60 checkpoint decides upgrade to High.
#BookBeautyAnywhere · #NeverDMForADate · Your Beauty, Perfected.