## Slide 1
LEISH.MY · LAUNCH MARKETING PLAN · 90 DAYS
Low Budget (Bootstrap)
Never DM for a Date Again. — official launch October 5, 2026
TOTAL BUDGET
RM 10,000
DAY-90 HEADLINE
300 clients · 25 artists · 6–10 bookings/wk
LAUNCH DATE
Oct 5, 2026
Founder-led quiet launch. Community, artist network, referrals and barter — near-zero paid. The goal is proof of unit economics, not scale.

## Slide 2
EXECUTIVE SUMMARY
The Play — Low Budget (Bootstrap)
FOCUS
Proof, not scale
Hit consistent weekly bookings at CAC ≤ RM 15 and artist retention ≥ 80% → unlock the Medium plan (RM 40k) for Q1'27 CNY season.
STYLE
Quiet soft launch
No event, no paid splash: waitlist email + organic posts + LEISH30 on Oct 5. Growth via bridal FB groups, campus and co-hosted pop-up.
GROWTH LOOP
People over ads
Artist share links (built into the product), referral from Day 1, nano-KOL barter, UGC contests. RM 2.5k retargeting only — no prospecting.
Artist gate: 20 bookable artists by Sep 28 · Offers: LEISH30 cap 100 · Free 6-month Pro for artists (compensates for lower traffic)

## Slide 3
RM 10,000 · 90 DAYS
Budget Breakdown
Community & events (co-hosted pop-up, campus, giveaways)
RM 3,000
30%
Meta ads — retargeting only (from week 2)
RM 2,500
25%
Nano KOLs — barter + commission (no big flat fees)
RM 1,500
15%
Artist acquisition (referral fees RM100 × 10)
RM 1,000
10%
Tools & design (Canva Pro, stock, ad tools)
RM 1,000
10%
Contingency
RM 1,000
10%
Payback logic: Organic-heavy CAC ≤ RM 15 → LTV RM 90–150 = 6–10x LTV:CAC. Paid is retargeting-only (closing), never prospecting, at this scale.

## Slide 4
NORTH-STAR METRIC: COMPLETED BOOKINGS PER WEEK
Day-90 Targets
300
Registered clients
25
Active artists & studios
6–10
Bookings / week
RM 1.8–3k
GMV / week
≤ RM 15
Blended CAC (organic-heavy)
1,200
Email list
PROGRESSION
KPI | Pre-launch | Day 30 | Day 60 | Day 90
Waitlist / clients | 400 waitlist | 120 | 220 | 300
Weekly bookings | — | 3–4 | 5–7 | 6–10
Commission / wk (20%) | — | RM 180 | RM 300 | RM 360–600
Email list | 600 | 800 | 1,000 | 1,200
Social following | 600 | 1,200 | 1,800 | 2,500

## Slide 5
TIMELINE
Four phases
PHASE 0 · PRE-LAUNCH
Aug 10 – Oct 4
Green-light Aug 10
Waitlist live Sep 7 (RM30 offer)
20 anchor artists, founder concierge
Founder content 3x/wk
No paid before Day 0
PHASE 1 · SOFT LAUNCH
Oct 5 – 11
Quiet launch: waitlist email + organic
LEISH30 live (cap 100)
Referral live Day 1 (RM15/RM15)
Pitch 5 wedding bloggers (free)
PHASE 2 · COMMUNITY GROWTH
Oct 12 – Dec 31
Bridal FB groups daily (value posts)
1 co-hosted pop-up (RM 1.5k)
Nano-KOL barter + UGC contest
1 blog/mo long-tail SEO
PHASE 3 · CHECKPOINT
Jan 2027
≥8 bookings/wk + CAC ≤ RM 15 +
artist retention ≥ 80% →
move to Medium (RM 40k)
for Q1'27 CNY season

## Slide 6
CHANNEL MIX
Owned · Paid · Earned
OWNED FIRST — ~85% OF THE WORK
IG — 3 posts + daily stories + 1 reel / wk
TikTok — 1–2 founder reels / wk
FB + bridal/beauty groups — daily, value-first
Email (Brevo) — sequence + 1 newsletter/mo
Artist share links — the #1 acquisition loop
Founder LinkedIn — weekly build-in-public posts
SEO — 1 long-tail blog/mo
PAID — RM 2.5K
Meta retargeting only, from week 2
Audiences: site visitors + waitlist abandoners
Creative: RM30 offer
No Google · No TikTok ads · No prospecting
Pause <1.5x ROAS after 2 weeks
EARNED + COMMUNITY — RM 5.5K
Nano KOLs (2k–20k) — barter + 10–15% of GMV
Ambassador program — top 10 clients, RM50/mo
1 co-hosted pop-up with partner studio
1 campus pop-up (Cyberjaya)
Bridal FB group giveaways (RM 500)
UGC contest — 5 × RM50 vouchers monthly

## Slide 7
LOCK BEFORE DAY 0
Launch Offers & Promotions
CLIENT SIDE (DEMAND)
LEISH30
RM30 off first booking · cap 100 · valid to Day 30
Refer-a-friend
RM15 credit each · live from Day 1
UGC contest
5 × RM50 vouchers · monthly
ARTIST SIDE (SUPPLY)
Free 6-month Pro listing
Normally RM 200–500/mo · cap 25 artists
0% commission, first 10 bookings
vs standard 20% · cap 15 artists
Artist referral
RM100 on referee's 5th booking · cap 10
⚠ Pre-launch dev task: verify promo-code / credit support in admin before Sep 7 (same as other tiers).

## Slide 8
WATCH WEEKLY
Risks & Mitigations
Demand too slow → artists churn
Free 6-month Pro; celebrate every booking publicly; weekly artist check-ins.
Founder bandwidth
2 batch content days/wk; templates; hire part-time helper from contingency if bookings justify.
No PR / low visibility
FB groups + campus + barter nano-KOLs; accept slower ramp — this tier buys proof, not reach.
Paid waste at tiny budget
Retargeting only; pause <1.5x ROAS after 2 weeks.
Promo abuse
One code per account; cap 100 redemptions.
Guardrails: artists idle 14+ days · no-show <15% · artist response <4 hrs · paid cost per booking < RM 40

## Slide 9
OWNER CHECKLIST + UPGRADE PATH
Execute · Measure · Decide
30-DAY CHECKLIST
Aug 10
Confirm date + budget
Sep 7
Waitlist + RM30 offer live
Sep 21
5 wedding bloggers pitched
Sep 28
20 anchor artists (gate!)
Oct 5
DAY 0 — soft launch
Oct 12
Retargeting ON (week 2)
UPGRADE / DOWNGRADE
Upgrade
Day-60: ≥8 bookings/wk + CAC ≤ RM 15 + artist retention ≥ 80% → move to Medium (RM 40k) for Q1'27 CNY season.
Hold
Day-90 GMV/wk < RM 1,500 → diagnose supply/checkout/demand before spending more.
REMAINING CHECKLIST
Nov 10
Co-hosted pop-up
Dec 4
Day-60 checkpoint
Jan 4
Day-90 review → upgrade decision
GA4/Meta events verified Sep 7 · referral live Oct 5 · founder batches content Mon + Thu.

## Slide 10
Prove it first.
Full plan: docs/launch-marketing-plan-low.md · Tiers: docs/launch-marketing-plan-tiers.md
Next step: run the 10-item founder checklist; the Day-60 checkpoint decides whether Leish! earns the Medium budget for CNY season.
#BookBeautyAnywhere · #NeverDMForADate · Your Beauty, Perfected.