## Slide 1
LEISH.MY · LAUNCH MARKETING PLAN · 90 DAYS
Never DM for a Date Again.
Malaysia's beauty booking marketplace — official launch October 5, 2026
TOTAL BUDGET
RM 96,000
DAY-90 TARGETS
25–30 bookings/wk · 60+ artists · 1,500 clients
LAUNCH DATE
Oct 5, 2026
Aligned with the FY26 financial forecast — Year-1 revenue RM 180–250k · 20% commission · avg booking RM 250–350

## Slide 2
EXECUTIVE SUMMARY
The Play
WHY
Beauty booking in Malaysia is broken
Clients DM 15 artists and wait days for a quote. Artists drown in DM chaos, ghosting and late payments. Nobody owns real-time MUA booking — that's Leish!'s wedge.
WHAT
A two-sided marketplace
Clients book vetted makeup artists & studios with real-time availability, instant confirmation and secure Billplz payment. Artists get portfolios, bookings, reminders and payouts.
HOW
Both sides, supply first
Recruit 30 anchor artists before Day 0 (critical path), then drive client demand through paid, KOLs, events and PR. Launch at the peak of wedding season.
Launch theme: Never DM for a date again
Artist theme: Get booked. Get paid.
Hero categories: Bridal · Hijab · Event

## Slide 3
POSITIONING
Two messages, one marketplace
TO CLIENTS
“Book Malaysia's top makeup artists & studios in minutes — real-time availability, instant confirmation, secure payment.”
TO ARTISTS & STUDIOS
“Get booked. Get paid. Your portfolio, your pricing, zero admin — we handle bookings, reminders and payments.”
WHAT THE PLATFORM ALREADY HAS — USE IT
Instant booking + Billplz payments
Real-time availability & reviews
Artist/studio profiles with portfolios
Rewards + Leish+ (RM29/mo) upsell
WhatsApp booking flow
Brevo email (hello@leish.my)
GA4 + Meta Pixel installed
Artist shareable profile links

## Slide 4
TIMELINE
Four phases, one launch
PHASE 0 · PRE-LAUNCH
Aug 10 – Oct 4
Waitlist live with RM30 offer
Recruit 30 anchor artists (concierge)
Teaser social 3x/wk + countdown
GA4/Pixel events + Brevo sequences
PHASE 1 · LAUNCH WEEK
Oct 5 – 11
“Never DM for a date again” campaign
KL launch pop-up + press event
Wave 1: 8–12 micro KOLs
Meta + Google paid ON, PR out
PHASE 2 · WEDDING SEASON
Oct 12 – Dec 31
Wave 2 KOLs + client UGC
Referral program live (Day 30)
Wedding expos + hijab push
B2B corporate + Leish+ pilot
PHASE 3 · REVIEW
Jan 2027
Score vs Day-90 targets
Cohort/LTV analysis
Q1'27 plan + expansion cities

## Slide 5
NORTH-STAR METRIC: COMPLETED BOOKINGS PER WEEK
Day-90 Targets
1,500
Registered clients
60+
Active artists & studios
25–30
Bookings / week
RM 7–9k
GMV / week
≤ RM 20
Client CAC (paid)
2.5–3.5x
Blended ROAS
KPI | Pre-launch | Day 30 | Day 60 | Day 90
Waitlist / clients | 2,000 waitlist | 600 | 1,000 | 1,500
Weekly bookings | — | 12 | 20 | 25–30
Commission revenue / wk (20%) | — | RM 700 | RM 1,200 | RM 1,500–1,800
Email list | 2,500 | 4,000 | 5,000 | 6,000
Social following | 3,000 | 6,000 | 8,000 | 10,000

## Slide 6
RM 96,000 · 90 DAYS
Budget Breakdown
Meta ads (IG + FB, incl. retargeting)
RM 29,000
30%
Influencers / KOLs (2 waves, 16–18 creators)
RM 24,000
25%
Google Search + PMax
RM 12,000
13%
Events — launch pop-up + wedding expos
RM 12,000
13%
TikTok ads (Spark on creator content)
RM 6,000
6%
Artist acquisition (ads + webinar)
RM 6,000
6%
Community / campus seeding
RM 4,000
4%
PR & media kit
RM 3,000
3%
Payback logic: blended CAC RM20 → client LTV RM 90–150 (2–3 bookings × RM 300 × 20%). CAC pays back in 1–2 bookings. Kill or scale by ROAS weekly — this is a growth test, not a burn.

## Slide 7
CHANNEL MIX
Owned · Paid · Earned
OWNED — foundation
Instagram — 4–5 posts + 10 stories + 2 reels / wk
TikTok — 3–4 UGC-style reels / wk
Facebook + bridal/beauty groups — daily participation
Email (Brevo) — lifecycle sequences + 2 newsletters/mo
WhatsApp API — confirmations, reminders, broadcasts
SEO — 2 blogs/mo on /inspiration + /events
Artist share links — every artist recruits clients
PAID — RM 47k
Meta (IG+FB) RM 24k — bridal/beauty interest stacks, KL-Selangor, 20–40
Google RM 12k — high-intent: “bridal makeup KL”, “MUA near me”
TikTok RM 6k — Spark Ads on creator content
Retargeting RM 5k — visitors, waitlist & cart abandoners, RM30 creative
Artist-side ads — target working MUAs (“switch from DM chaos”)
EARNED + COMMUNITY — RM 43k
2 KOL waves — 16–18 micro/mid creators, flat + booking-code commission
1–2 wedding expos + KL launch pop-up (glam bar)
PR — SAYS, The Star, Malay Mail, NST, wedding blogs
Giveaways in bridal FB groups
Campus pop-ups — Cyberjaya (MMU, Limkokwing, UPM area)
Free “grow your MUA business” webinar (Nov)

## Slide 8
LOCK BEFORE DAY 0
Launch Offers & Promotions
CLIENT SIDE (DEMAND)
LEISH30
RM30 off first booking · cap 300 · valid to Day 30
Early-bird bonus
Waitlist members get RM30 + priority access
Refer-a-friend
RM20 credit each · live from Day 30
ARTIST SIDE (SUPPLY)
Free 3-month Pro listing
Normally RM 200–500/mo · cap 50 artists
0% commission, first 10 bookings
vs standard 20% · cap 30 artists
Artist referral
RM100 + featured slot when referee hits 5 bookings
⚠ Pre-launch dev task: verify promo-code / credit support in admin. If unsupported, use UTM + support-issued credits and log a dev task before Aug 24.

## Slide 9
FIRST 12 WEEKS
Content Calendar — Highlights
Week | Theme | Hero content | Campaign
W1 · Aug 10 | Tease | Founder story reel — “Why we built Leish!” | Waitlist open
W2 | Artist spotlight | “Meet the artist” carousels ×3 | Artist recruitment
W3 | Pain-point comedy | “POV: DM-ing 15 MUAs for your wedding date” | Waitlist
W4 | Education | Bridal makeup cost guide KL 2026 | Waitlist
W5 | Proof | Beta client before/after + testimonial | Waitlist
W6 | Countdown | “Leish! launches Oct 5” series | Launch hype
W7 · Oct 5 | LAUNCH WEEK | Event content, KOL posts, LEISH30 code | DAY 0
W8 | Social proof | UGC roundup + first bookings | Post-launch
W9 | Hijab series | Hijab MUA directory + looks | Community
W10 | Wedding season | “Book your wedding MUA now” urgency | Paid push
W11 | Referrals | Refer-a-friend launch creative | Referral
W12 | Festive prep | CNY / Raya early-bird booking | Festive
Evergreen SEO (2/mo): “Best Bridal Makeup Artists in KL & Selangor 2026” · “How Much Does Bridal Makeup Cost in Malaysia?” · “Hijab Makeup Looks for Weddings” · “10 Questions to Ask Your MUA”

## Slide 10
WATCH WEEKLY
Risks & Mitigations
Risk | L | I | Mitigation
Not enough artists at launch | Med | High | Concierge recruitment from T-6; 30-artist gate — delay Day 0 if short
Demand lags supply (artists churn) | Med | High | Weekly zero-booking check; demand ads + featured rotation; commission-free period
Checkout friction (Billplz) | Med | High | Track booking_started→completed; A/B deposit vs full payment; WhatsApp assist
KOL underperformance | Med | Med | 60/40 flat + booking commission; test 4 in wave 1 before wave-2 spend
Promo abuse (RM30 codes) | Med | Low | One code per account; cap 300; fraud flag on repeat emails
SEO ramp too slow | High | Low | Content engine from Day 1; treat SEO as 6-month play; rely on paid + social at launch
Traffic spike / infra | Low | High | Launch-ready ✅; load-test /artists + /bookings; UPSTASH Redis in prod
Guardrails: artists idle 14+ days · no-show/cancellation <15% · artist response <4 hrs · search→booking ≥2%

## Slide 11
30-DAY LAUNCH CHECKLIST
Owner Matrix
Aug 10
Confirm launch date + sign-off on plan
Aug 17
Hire/assign marketing lead + content creator
Aug 24
Waitlist page live + RM30 offer configured
Aug 24
GA4 + Meta events verified (10 events)
Aug 31
Brevo sequences + UTM scheme live
Sep 21
Media kit + press release drafted
Sep 21
KOL wave 1 contracted (8–12)
Sep 21
Launch pop-up venue + invite list
Sep 28
30 anchor artists recruited (gate!)
Sep 28
Paid campaigns live (test) → full Oct 5
Oct 5
DAY 0 — official launch
Nov 4
Referral live · wedding expo booked · Day-30 review
Dec 4
Leish+ pilot to top clients
Jan 4
Day-90 review + Q1'27 plan

## Slide 12
CLOSE BY AUG 10
Open Questions for the Founder
1
Confirm launch date
Oct 5, 2026 proposed — first Monday after Hari Malaysia week, peak wedding season.
2
Budget sign-off
RM 96,000 / 90 days, drawn from seed runway per financial forecast.
3
Promo-code system
Does admin support codes/credits, or is a dev task needed before Aug 24?
4
Marketing owner
In-house hire vs agency vs founder-led with this plan as the ops doc — #1 dependency.
5
Brand assets
IG/TikTok/FB handles (@leish.my?), logo kit, press photos.
6
Leish+ timing
Keep RM29/mo pilot internal for 90 days; public in Q1'27 (recommended).
7
Legal & compliance
PDPA consent on waitlist capture + contest T&Cs before any giveaway.

## Slide 13
WEEKLY DASHBOARD, EVERY MONDAY
Measurement & Attribution
EVENTS TO VERIFY (GA4 + META)
waitlist_signup
sign_up
search
view_artist
booking_started
booking_completed (value = booking value)
payment_success
artist_application_started
share_link_clicked
WEEKLY DASHBOARD SECTIONS
Growth — waitlist, signups, artists, bookings, GMV, commission
Funnel — search → artist view → booking_start → complete
Paid — spend, ROAS, CAC, CPM/CPC by channel
Quality — no-show, cancellation, avg rating, repeat rate
Content — email list, opens/clicks, reach, top posts
ATTRIBUTION
UTM on every outbound link — source / medium / campaign / term / content (scheme in plan Appendix C). Capture source at signup. Report: bookings & CAC by channel.

## Slide 14
Ready to glow.
Full plan: docs/launch-marketing-plan.md · Summary: docs/launch-marketing-plan-summary.md
Next step: close the 7 blockers by Aug 10, then execute the 30-day checklist.
#BookBeautyAnywhere · #NeverDMForADate · Your Beauty, Perfected.